# Task Prompt

You are the newly hired Digital Learning Experience Project Manager at the Center for Teaching Innovation (CTI) at Ashgrove University. Your director, Dr. Elena Vasquez, has asked you to produce a Project Design & Pilot Plan for a new tool: a low-stakes, GenAI-assisted “debugging sandbox” for CS1 students, aimed at reducing reliance on AI-generated fixes that students don’t understand.

You have been given five source materials, attached below. Use them as your evidence base — do not invent misconception statistics, survey results, or prior-tool findings that aren’t in the packet, and do not contradict anything stated in them.

- 01_directors_memo.md — the commissioning memo, including hard constraints on budget, timeline, staffing, vendor, integration approach, and policy compliance.

- 02_misconception_research_brief.md — internally coded frequency data on 8 CS1 misconception categories.

- 03_prior_tools_audit.md — a heuristic-evaluation audit of two prior AI debugging tools and why each failed.

- 04_student_survey_results.md — quantitative and qualitative student survey data on AI tool use, low-stakes practice, and gamification.

- 05_ux_heuristics_reference.md — Nielsen’s 10 usability heuristics, provided as a reference list only.

## Your deliverable

Write a single Project Design & Pilot Plan document, using exactly these nine section headings, in this order:

- Executive Summary (200 words or fewer)

- Problem Statement & Misconception Targeting

- Lessons from Prior Tools

- Tool Concept & UX Design

- GenAI Guardrail Design

- Project Plan (timeline, roles, budget)

- Risk Register

- Evaluation & Success Metrics

- Accessibility, Equity & Privacy

## Requirements

- The plan must be internally consistent and must satisfy every hard constraint in the director’s memo simultaneously — budget, timeline, staffing, vendor, integration approach, and policy. Do not propose working around a constraint (e.g., requesting more budget, a different vendor, or a new LTI integration); design within them.

- Ground your misconception targeting and tool design explicitly in the data provided — cite the specific categories, frequencies, prior-tool failures, and survey findings you’re drawing on.

- When you apply a UX heuristic, name it and tie it to a specific, concrete design decision — don’t just assert the tool will be “intuitive” or “user-friendly.”

- The GenAI guardrail design must directly address the specific over-reliance and engagement-collapse failure modes documented in the prior-tools audit.

- Budget must be itemized and must not exceed the stated cap. Timeline must fit the stated build and pilot windows exactly.

- Write as a real deliverable meant to be read and approved by the Associate Dean — not as an essay about the topic in general.

Produce the complete document now.